## Taskmaster
Taskmaster
Date | Week Of: | Task | Owner | Workstream | Completed? | Notes
2017-04-04 | 2017-04-03 | Draft Confirmation/Travel Scholarship App. Copy | Bobby | Logistics - People | Completed
2017-04-05 | 2017-04-03 | PEER: Confirmation/Travel Scholarship App. Copy | ORG Team | Logistics - People | Completed | By EOD
2017-04-05 | 2017-04-03 | Curriculum Worksheets sent to Presenters | Jalakoi/JW/TW | Curriculum | Completed | by EOD
2017-04-05 | 2017-04-03 | Draft Confirmation Email (include with built out form) | Bobby/Jalakoi | Logistics - People | Completed
2017-04-05 | 2017-04-03 | Final List of Venues | Kevin | Logistics - Venue | Completed | By EOD
2017-04-07 | 2017-04-03 | REVIEW: Confirmation/Travel Scholarship form | ORG Team | Logistics - People | Completed | BY 12pm
2017-04-07 | 2017-04-03 | RSVP: Deadline | Bobby | Logistics - People | Completed
2017-04-08 | 2017-04-03 | Confirmation form sent out |  | Logistics - People | Completed
2017-04-10 | 2017-04-10 | DUE: Presenter Worksheets completed (by volunteers) Begin setting up curriculum coaching calls with presenters | Jalakoi/KR/DJ | Curriculum | Completed | Start Staff workstream for Curriculum
2017-04-12 | 2017-04-10 | LOCKED: Venue (still need to submit COI) | Kevin | Logistics - Venue | Completed
2017-04-12 | 2017-04-10 | Mid-Process Tier of Travel Scholarship applicants | Bobby/Traci/Jenn/Mary | Logistics - People | Completed
2017-04-13 | 2017-04-10 | Reminder Email: Confirmation/Travel Scholarship | Bobby | Logistics - People | Completed | To people who have not yet completed the form
2017-04-14 |  | First round of curriculum coaching calls complete | Jalakoi | Curriculum | Completed
2017-04-16 | 2017-04-10 | Confirmation/Travel Scholarship Deadline | Bobby | Logistics - People | Completed
2017-04-17 | 2017-04-17 | REVIEW: Proposal on travel scholarships | Bobby | Logistics - People | Completed
2017-04-17 | 2017-04-17 | Email: Confirmation of summit -- Venue announcement/potential hotels | Bobby/Kevin | Logistics - People | Completed
2017-04-18 | 2017-04-17 | Book Travel Begins | Mary | Logistics - People | Completed | Continuous process: • Hours between 2-5 for booking for approvals • Book tier 1's, then tier 2's, tier 3's, tier 4's, then tier 5 • Once a flight is approved by (TW/JW), send itinerary for confirmation with 24 hour deadline to scholarship to volunteer • Update the tracker with the final price
2017-04-19 | 2017-04-17 | One Month Out -- Travel Schol appr; agenda-goals locked; curriculum outlines done; logistics locked; Final Month-- dry runs, walk thrus, supplies/food ordered | ORG Team | Logistics - People | Completed
2017-04-19 | 2017-04-17 | Decision letters for travel scholarships | Mary | Logistics - People | Completed | To those not selected
2017-04-21 |  | First Draft Content, Activities, Tick Tock for each session | Org Team | Curriculum | Completed
2017-04-24 |  | Org Team (minus JW/TW) meeting to finalize Content, Tick Tock for each session | Org Team | Curriculum | Completed
2017-04-24 | 2017-04-24 | Travel Scholarship budget/process checkin | Bobby/Mary | Logistics - People | Completed | Check-in on budget, where we're at on taking waitlisted people on, etc..
2017-04-24 | 2017-04-24 | Travel Scholarship budget/process checkin |  | Logistics - People | Completed
2017-04-25 |  | Curriculum Presented to Full Team at Summit Meeting | Org Team | Curriculum | Completed
2017-04-25 |  | Summit Design and Printing Assets planning meeting | Kevin | Logistics - Venue | Completed | nametags, agenda, breakout worksheets, welcome letter, banners
2017-04-26 | 2017-04-24 | Travel Scholarships Locked | Bobby | Logistics - People | Completed
2017-04-27 |  | Travel Itineraries Sent Out with hotel reminder | Bobby | Logistics - People | Completed
2017-04-27 |  | Full Annotated Agendas due to Jalakoi | Jalakoi | Curriculum | Completed
2017-04-28 |  | Welcome Packet first draft complete | Kevin | Logistics - Venue | Completed
2017-05-01 |  | Welcome Packet sent to training peer | Kevin | Logistics - Venue | Completed | add brainstorm, proposals, review benchmarks for all venue items, lanyards
2017-05-01 |  | Preview email on the agenda | Bobby | Logistics - People | Completed | Profile of volunteer trainers, "meet staff and their favorite places," agenda preview.
2017-05-01 |  | 1 Draft of Curriculum Due - Ready to send to Peer (slides, PP, worksheets, all copy) | Jalakoi | Curriculum | Completed
2017-05-03 |  | Catering proposal started | Mary | Logistics - Venue | Completed
2017-05-03 |  | PEER: Curriculum Complete By 12noon, all worksheets then sent to Words | Org Team | Curriculum | Completed
2017-05-04 |  | Welcome Packet copy sent to David | Kevin | Logistics - Venue | Completed
2017-05-04 |  | REVIEW: Curriculum Due COB | Jalakoi | Curriculum | Completed
2017-05-05 |  | Week of 5/1 - 5/5: first Dry Runs completed | Org Team | Curriculum | Completed
2017-05-05 |  | Major design assets ordered | David | Logistics - Venue | Completed | banners, placards, etc.
2017-05-07 |  | All copy/PPs/Materials reviewed and approved to send to David | Jalakoi | Curriculum | Completed
2017-05-08 |  | Curriculum materials sent to David to begin design | Jalakoi | Curriculum | Completed
2017-05-08 |  | Supply checklist proposed | Kevin | Logistics - Venue | Completed
2017-05-09 |  | Welcome Packet sent to all attendees | Kevin | Logistics - Venue | Completed
2017-05-08 |  | Catering proposal complete | Mary | Logistics - Venue | Completed
2017-05-09 |  | Staffing grid proposed | Michelle | Logistics - Venue | Completed
2017-05-10 |  | Staffing grid approved | Michelle | Logistics - Venue | Completed
2017-05-10 |  | Supply checklist approved | Kevin | Logistics - Venue | Completed
2017-05-10 |  | Catering order approved | Kevin | Logistics - Venue | Completed
2017-05-12 |  | Week of 5/8 - 5/12: second Dry Runs completed | Org Team | Curriculum | Completed
2017-05-12 |  | All curriculum materials designed and finalized | Jalakoi/David | Curriculum | Completed
2017-05-15 |  | Email Final PPs to presenters | Jalakoi | Curriculum | Completed
2017-05-12 |  | All supplies ordered | Kevin | Logistics - Venue | Completed
2017-05-12 |  | Printing needs ordered | Katie | Logistics - Venue | Completed
2017-05-15 |  | Event walk-through | Kevin | Logistics - Venue | Completed | check with Charise
2017-05-15 |  | Catering order submitted | Mary | Logistics - Venue | Completed
2017-05-15 |  | Worksheets, agendas, etc. printed | Katie | Logistics - Venue | Completed
2017-05-17 |  | Confirmations of attendees (email and phone) | Bobby | Logistics - People | Completed | Divide list among Mary, Adrian, Bobby/available org team members
2017-05-18 |  | Event folders stuffed and taken to venue | Kevin | Logistics - Venue | Completed
2017-05-19 |  | Third and Final Dry Run with Panelists before the Reception (5pm) | Jalakoi | Curriculum | Completed
2017-05-19 |  | Open House at OFA HQ | Kevin | Logistics - Day of Summit | Completed | save the dates, agenda, roles
2017-05-20 |  | Day 1: Leadership Summit | Kevin | Logistics - Day of Summit | Completed
2017-05-21 |  | Day 2: Leadership Summit | Kevin | Logistics - Day of Summit | Completed
Yay!
This work is licensed under the Creative Commons Attribution-NonCommercial 4.0 International License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/4.0/ or send a letter to Creative Commons, PO Box 1866, Mountain View, CA 94042, USA

## Agenda
Time | Session | Trainer | PPT/Materials done? | Notes
2017-05-20
9:00 -- 9:45 | Registration | Everyone!
10:00 -- 10:35 | Logistics and Agenda | Emcee | No
10:35 -- 11:20 | State of OFA | Jen/Katie Hogan | No
11:20 -- 11:40 | Movement/Break
11:40 -- 1:00 | Panel Breakout 1 | Panelists & Moderators | No
| Long-Term Organizers/Building Sustainable Chapters/Power of Training | Bill Davis Sarah Horan Cindy Lay Hope Busto-Keys | No
| Mobilizing Best Practices | Scott Cross Linda Hemenway | No
| Leading through Fellowship (Campus and Community Fellows) | Victoria Wilson Mona DeQuis | No
1:00 -- 1:50 | Lunch
2:10 -- 3:30 | Panel Breakout 2 | Panelists & Moderators
| Building Strong Coalitions/Working with Elected Officials | Paul Geenen Lexie Weaver Linda Porter Cheryl Laux | No
| Local Issue Organizing | Mr Page Kyoko Takayama Martha Clark | No
| Leading through Fellowship (Campus and Community Fellows) | Victoria Wilson Mona DeQuis | No
3:30 - 3:50 | Movement/Break
3:50 -- 5:00 | State Base/Training Program Breakout
| Red State | DeAndre Jones | No
| Blue State | Katie Robbins | No
| Purple State | Jalakoi Solomon | No
| Fellows Manager Kick Off | Bobby Brady | No
5:00 -- 5:30 | Debrief and Close |  | No
2017-05-21
9:00 -- 9:15 | Intro | Emcee | No
9:15 -- 9:40 | We Are OFA: Meet the Movement | Campus - (Jessica Salas) Fellowship - (Christina Lopez) Chapter Leader - (Tiffany Alegretti) Alumni - Anna (PA) HQ Staffer/Campaign - (Jack Shapiro) | No | Next Steps - Email - 4 min, 12 slides, 20 seconds each (send an example) - "You have a great story to share,
9:40 -- 10:10 | Issue Update | Jack Shapiro | No
10:10 -- 10:30 | Break/Movement
10:30 -- 12:00 | Workshops and Office Hours
| National Issues/Coalition Building | Jack Shapiro | No
| Digital Tools/Best Practices | Digi Team (TBD) | No
| Building New/Official Chapters | Org Team (TBD) | No
12:00 -- 12:10 | Break/Movement
12:10 -- 12:30 | Debrief and Close |  | No
Staff Volunteers
Yoli
Sammi | Saturday morning
Robert
Reggie
Jeff | Multimedia
Justin | Multimedia
Abby | Multimedia
Alex Woodward | Multimedia (when possible)
Staff
Mary | Lunch
Alexis

## Printing List
Printing Checklist
Item Name | Quantity | Vendor | Ordered? | Printed?
Folders / Sign-in:
Agenda | 200 | FedEx | Yes | Yes
We are OFA | 200 | FedEx | Yes | Yes
Welcome Letter | 200 | FedEx | Yes | Yes
Meet the Trainers | 200 | FedEx | Yes | Yes
Notes Page | 200 | FedEx | Yes | Yes
Name tags | 200 | David's Printer | Yes | Yes
Internal:
Staffing Grid | 15 | In house | Adrian | Yes
Tick Tocks | 15 | In house | Adrian | Yes
Time Cards | 5 | In house | Yes | Yes
Photo releases | 10 | In house | David
Interview Time Slots | 5 | In house | Adrian | Yes
Room Assignments | 15 | In house | Adrian | Yes
Summit Checklist | 15 | In house | Adrian | Yes
Way finding:
Registration Table | 1 | In house | Yes | Yes
Photobooth | 1 | In house | Yes | Yes
Executive Room | 1 | In house | Yes | Yes
Classroom 1 | 1 | In house | Yes | Yes
Classroom 2 | 1 | In house | Yes | Yes
Main Hall | 1 | In house | Yes | Yes
Breakouts:
FM Workbook | 45 | FedEx | Yes | Yes
Building Coalitions | 50 | FedEx | Yes | Yes
Coalitions 101 | 75 | FedEx | Yes | Yes
Sustainable Chapters: Key Takeaways | 75
Sustainable Chapters Worksheet | 75 | FedEx | Yes | Yes
Training/Coaching Debrief | 125 | FedEx | Yes | Yes
Training/Coaching Instructions | 125 | FedEx | Yes | Yes
Training/Coaching Observer | 35 | FedEx | Yes | Yes
Catgrid | 35 | FedEx | Yes | Yes
Blank grid | 35 | FedEx | Yes | Yes
Purple States | 50 | FedEx | Yes | Yes
Tweeting | 50 | FedEx | Yes | Yes
Twitter List | 50 | FedEx | Yes | Yes
Twitter Relationships | 50 | FedEx | Yes | Yes

## Tick Tock - Open House
OFA Summit Series: Meeting of the Movement - Tick Tock (Open House)
Start Time | End Time | Room | Section | Point Person | Helpers | Notes
11:30 | 14:30 | Venue | Summit Set-up
|  |  | Bring registration folders, Event signs, Agendas, timecards, logo banners, nametags (including a few blank ones), water cups, breakout handouts, butcher paper, pens, markers, masterlist of where everyone should bring, all supplies | Kevin | David
Jalakoi
Michelle
Adrian
|  |  | Test AV in all the rooms | Kevin
|  |  | Distribute butcher paper and markers to breakout rooms | Katie
|  |  | Supply Runners | Bobby | Michelle
15:00 | 16:00 | OFA HQ | HQ Set-up/Clean-Up
|  |  | Clean off working area | Bobby | All staff
Kitchen cleanup (putting away of dishes)
|  |  | Keg duty / Wine duty / Cooler | Katie
Guest Wifi password available
|  |  | Food set-up | Mary | Michelle
Trashcans in helpful places
|  |  | Set up Merch Table | Kevin | DeAndre
17:00 | 18:00 | HQ Offices | Summit Dry-Runs
|  |  | Presentation/Breakout Dry-runs | Jalakoi |  | Katie, Jalakoi, DeAndre, Kevin, Bobby, Jen, Traci, Michelle
18:00 | 21:00 | OFA HQ | Open House
0:00 |  | Lobby | Registration desk (20 minute shifts) | Robert | Jalakoi | Shift 1: Robert, Jalakoi; Shift 2: Kibo, Adrian; Shift 3: Mary; Shift 4: Kevin; Shift 5: Bobby; Shift 6: Katie; Shift 7: Michelle; Shift 8: DeAndre
|  | At office door | Greeter (20 min shifts) | Michelle | Bobby | Shift 1: Michelle; Shift 2: Bobby; Shift 3: Katie
0:00 |  | Floating | Photo taker | David | Digital Team
|  | Conference Room | Merch Table (30 minute shifts) | Kevin | DeAndre | Shift 1: Kevin, Shift 2: DeAndre
21:00 | 21:45 | OFA HQ | Clean up of HQ
|  |  | Clean up any trash | All Staff
|  |  | Printed sheets for sign-in |  |  | Abby, Kibo, Justin
Print off shift grid

## Tick Tock - Day 1
OFA Summit Series: Meeting of the Movement - Tick Tock (Day 1)
Start Time | End Time | Room | Section | Point Person | Helpers | Notes
8:00 | 9:00 | Sitewide | Set-up, Sign-in & Breakfast
8:00 | 8:10 |  | Staff Arrive | Org Team |  | Go to the Staff Meeting Room
8:10 | 8:30 |  | Supply the rooms (butcher paper, wayfinder signs, laptops, HDMI cords, wifi password, arrows, signs and snacks) | Kevin | Alexis, Jalakoi, Michelle
8:10 | 8:30 |  | Design the rooms (banners, placards, tables, chairs, snacks) | Traci | Adrian, David, Katie | Main hall, lounge/cafe area, breakout rooms, placard wall for photos
8:10 | 8:30 |  | AV Set-up / Sound Test | Bobby | DeAndre, Reggie
8:10 | 8:30 |  | Story booth set up | David | Media Team
8:00 | 8:30 |  | Set-up Registration Tables | Bobby | Sammi, Robert, Yoli, Alexis, Elizabeth | 3 sign-in tables, 1 folder table -- direct them to photobooth
8:00 | 8:30 |  | Set up Music playlist | Michelle | Reggie | iPad spotify
8:30 | 8:40 |  | Final Run Through | Jalakoi | Kevin, Bobby, Michelle
8:30 | 8:50 |  | Breakfast Arrives / Set-up snacks | Mary | Reggie, Adrian, DeAndre
9:00 | 10:00 | Entrance | Arrival and Sign-in
9:00 | 10:00 |  | Register and sign-in guests | Bobby | Sammi, Robert, Yoli, Alexis, Elizabeth | Bobby greets at door. Sammi, Robert, Katie at register tables. Alexis at folder table
9:00 | 10:00 |  | Story booth | David | Full Media Team
9:00 | 10:00 |  | Story booth Tracker | Alex W |  | Registration Form Added column
9:00 | 10:00 |  | Lounge Greeters | Traci | Jenn, Bobby, Michelle
9:30 | 10:00 |  | Main Hall Greeters | Kevin | Jalakoi, Katie | Be in main hall by 9:30am
9:30 | 10:00 |  | Snack / Table Directors | Mary | DeAndre, Reggie, Adrian | Be in main hall by 9:30am
10:00 | 10:35 | Main Hall | Welcome & Intro
|  |  | Introduction presentation | Kevin
0:00 |  |  | Photo taker | Justin / Alex S
|  |  | Time keeper | Michelle
10:35 | 11:20 | Main Hall | State of OFA
|  |  | State of OFA presentation | Jen Warner/Katie Hogan
0:00 |  |  | Photo taker | Justin / Alex S
0:00 |  |  | Time keeper | Adrian
10:50 | 11:20 | Breakout Rooms | Break Out Rooms Set Up and Prep
|  | Executive | Leadership through Training & Coaching | Bobby & Kevin | Mary
|  | Main Hall | Long-term Organizing | Jalakoi | Alexis
|  | Classroom 1 | Mobilizing Best Practices | Michelle | Reggie
11:20 | 11:40 | Sitewide | Break
|  |  | Staff directing foot traffic | DeAndre (Main Hall) | Alexis (Lounge/Cafe)
11:40 | 13:00 | Breakout Rooms | Breakout Sessions #1
|  |  | Leadership through Training & Coaching presentation | Bobby/Kevin |  | Presenters: Bobby Brady, Kevin Lane, Victoria Wilson, Mona DeQuis
|  |  | Time Keeper | Alexis | *Timekeepers: Have list of vols scheduled for interview @ photo booth | *Give instructions for lunch. Group A leave room, head straight to lunch, everyone else to main hall to wait for your group to be called
|  |  | Long-term Organizing presentation | Hope Busto-Keyes |  | Presenters: Bill Davis, Sara Horan, Cindy Lay, Hope Busto-Keyes
|  |  | Time Keeper | Jalakoi | *Timekeepers: Have list of vols scheduled for interview @ photo booth | *Give instructions for lunch. Group A leave room, head straight to lunch, everyone else to main hall to wait for your group to be called
|  |  | Mobilizing Best Practices presentation | Michelle |  | Presenters: Scott Cross, Linda Hemenway
|  |  | Time Keeper | Katie | *Timekeepers: Have list of vols scheduled for interview @ photo booth | *Give instructions for lunch. Group A leave room, head straight to lunch, everyone else to main hall to wait for your group to be called
|  |  | Photo Takers | Justin | Alex S | Roam all rooms and take numerous photos
|  |  | Interview Runners | Abby | Jeff
12:15 | 13:00 | Entrance | Lunch Prep
|  |  | Catering set up | Mary | Reggie, DeAndre, Elizabeth
13:00 | 13:50 | Entrance | Lunch
|  |  | Available for questions | All Staff
|  |  | Staff directing foot traffic | All Staff | All Staff
13:15 | 13:30 | Staff Room | Staff Slice
All Staff
13:30 | 13:50 | Breakout Rooms | Break Out Rooms Set Up and Prep
|  | Executive | Leading through Training & Coaching | Bobby | Jalakoi, Elizabeth
|  | Main Hall | Building Strong Coalitions | Katie | Alexis
|  | Classroom 1 | Local Issue Organizing | DeAndre | Mary
13:50 | 14:10 | Main Hall | Icebreaker #1
|  |  | Take a slice from attendees. Pull out anecdotes. Direct to breakouts | Kevin
|  |  | Time Keeper | Michelle
14:10 | 14:30 | Entrance | Lunch Clean Up
|  |  |  | Mary | Reggie, DeAndre, Elizabeth
14:10 | 15:30 | Breakout Rooms | Breakout Sessions #2
|  | Executive | Leading through Training & Coaching presentation | Bobby/Kevin |  | Presenters: Bobby Brady, Kevin Lane, Victoria Wilson, Mona DeQuis
|  |  | Time Keeper | Jalakoi | *Timekeepers: Have list of vols scheduled for interview @ photo booth
0:00 |  | Main Hall | Building Strong Coalitions | Katie
|  |  | Time Keeper | Alexis | *Timekeepers: Have list of vols scheduled for interview @ photo booth
0:00 |  | Classroom 1 | Local Issue Organizing | DeAndre |  | Presenters: Paul Geenen, Lexie Weaver, Linda Porter, Cheryl Laux
|  |  | Time Keeper | Elizabeth | *Timekeepers: Have list of vols scheduled for interview @ photo booth
|  |  | Photo Takers | Justin | Alex S | Roam all rooms and take numerous photos
|  |  | Interview | Abby | Jeff
15:00 | 15:30 | Breakout Rooms | Break Out Rooms Set Up and Prep
|  | Classroom 2 | Red States | DeAndre (Michelle) | Mary, Elizabeth
15:30 | 15:45 | Main Hall | Ice Breaker #2
|  |  | Human Rock Paper Scissors | Kevin
15:50 | 17:00 | Breakout Rooms | Breakout Sessions #3
|  |  | Red States presentation | DeAndre
|  |  | Time Keeper | Kevin | *Timekeepers: Have list of vols scheduled for interview @ photo booth | Identify people to be interviewed during your slot
0:00 |  |  | Blue States presentation | Katie/Michelle
|  |  | Time Keeper | Alexis | *Timekeepers: Have list of vols scheduled for interview @ photo booth | Identify people to be interviewed during your slot
|  |  | Purple States presentation | Jalakoi
|  |  | Time Keeper | Mary | *Timekeepers: Have list of vols scheduled for interview @ photo booth | Identify people to be interviewed during your slot
|  |  | Fellows Manager Orientation | Bobby
|  |  | Time Keeper | Elizabeth | *Timekeepers: Have list of vols scheduled for interview @ photo booth | Identify people to be interviewed during your slot
|  |  | Photo Takers | Justin | Jeff, Abby, Alex S | Roam all rooms and take numerous photos
17:00 | 17:30 | Main Hall | Debrief & Close
|  |  | Debrief Day 1 | Kevin
|  |  | Photo taker | David
|  |  | Time keeper | DeAndre
|  |  | Mic runner | Michelle/Katie
17:30 | 17:40 | Main Hall | Group Photo
17:30 | 18:00 | Sitewide | Clean-up/Prep for day 2
|  |  | Clean up | Michelle | All Staff
|  |  | Situating the room for day 2 (placards, tables, chairs, snacks) | Kevin | All Staff

## Tick Tock - Day 2
OFA Summit Series: Meeting of the Movement - Tick Tock (Day 2)
Start Time | End Time | Room | Section | Point Person | Helpers | Notes
8:00 | 9:00 | Cafe / Main Hall | Set-up, Sign-in & Breakfast
8:00 |  |  | Staff Arrive | Org Team |  | Go to the Staff Meeting Room
8:05 | 8:30 |  | Supply the rooms (butcher paper, wayfinder signs, laptops, HDMI cords, wifi password, arrows, signs and snacks) | Kevin | Alexis, Jalakoi, Michelle
8:05 | 8:30 |  | Design the rooms (banners, placards, tables, chairs, snacks) | Traci | David, Katie | Main hall, lounge/cafe area, breakout rooms, placard wall for photos
8:15 | 8:30 |  | AV Set-up / Sound Test | Bobby | Reggie, DeAndre
8:15 | 8:30 |  | Final Run Through | Jalakoi | Kevin, Bobby, Michelle
8:30 | 8:50 |  | Photobooth set up | David | Media Team
|  |  | Set-up Registration Tables | Bobby | Sammi, Robert, Yoli, Alexis, Elizabeth | 3 sign-in tables, special cases
|  |  | Set-up music playlist | Michelle | Reggie
|  |  | Breakfast Arrives / Set-up snacks | Mary | Reggie, DeAndre
8:30 | 9:00 | Entrance | Arrival and Sign-in
|  |  | Register and sign-in guests | Bobby | Sammi, Robert, Yoli, Alexis, Elizabeth | Bobby greets at door. Sammi, Robert, Katie at register tables.
|  |  | Photobooth | David | Full Media Team
|  |  | Photobooth Tracker | Alex W
|  |  | Lounge Greeters | Traci | Jenn, Bobby, Michelle
|  |  | Main Hall Greeters | Kevin | Jalakoi, Katie | Be in main hall by 9:30am
|  |  | Main Hall Snack / Table Directors | Mary | DeAndre, Reggie | Be in main hall by 9:30am
9:00 | 9:15 | Main Hall | Welcome & Intro
|  |  | Intro presentation | Kevin
|  |  | Time keeper | Alexis
|  |  | Photo Takers | Alex S |  | Roam all rooms and take numerous photos
|  |  | Interview | Jeff
9:15 | 9:40 | Main Hall | Meet the Movement
|  |  | Meet the Movement presentation | Traci |  | Presenters: Campus - (Jessica Salas), Fellowship - (Christina Lopez), Chapter Leader - (Tiffany Alegretti), Alumni - Anna (PA), HQ Staffer/Campaign - (Jack Shapiro)
0:00 |  |  | Time keeper | Alexis
0:00 |  |  | Photo Takers | Alex S |  | Roam all rooms and take numerous photos
|  |  | Interview | Jeff
9:35 | 10:00 | Breakout Rooms | Break Out Rooms Set Up and Prep
|  | Executive Room | National Issues / Coalition Building | Jalakoi | DeAndre
|  | Classroom 1 | Mobilzing vs. Organizing: The Digital Way | Alex / Kibo | Elizabeth
|  | Classroom 2 | Fellows Manager Orientation | Bobby | Mary
|  | Main Hall | Becoming Official Chapters | Michelle | Katie
9:40 | 10:10 | Main Hall | Issues Update
|  |  | Issues Update presentation | Jenn
|  |  | Time keeper | Mary
|  |  | Photo taker | Jeff / Alex S
10:10 | 10:30 | Sitewide | Break
|  |  | Staff directing foot traffic | All Staff
10:30 | 12:00 | Breakout Rooms | Breakout Sessions #1
|  |  | National Issues / Coalition Building presentation | Jenn
|  |  | Time Keeper | Jalakoi | *Timekeepers: Have list of vols scheduled for interview @ photo booth
|  |  | Mobilzing vs. Organizing: The Digital Way presentation | Alex W
|  |  | Time Keeper | Elizabeth | *Timekeepers: Have list of vols scheduled for interview @ photo booth
0:00 |  |  | Fellows Manager Orientation | Bobby
|  |  | Time Keeper | Mary | *Timekeepers: Have list of vols scheduled for interview @ photo booth
0:00 |  |  | Becoming Official Chapters | Traci
|  |  | Time Keeper | Katie | *Timekeepers: Have list of vols scheduled for interview @ photo booth
|  |  | Photo Takers | Jeff | Alex S | Roam all rooms and take numerous photos
12:00 | 12:10 | Sitewide | Break
|  |  | Staff directing foot traffic | All Staff
12:10 | 12:40 | Main Hall | Debrief & Close
|  |  | Close Day 2 | Kevin |  | Needs: photo taker, possibly a mic runner
|  |  | Time keeper | Mary
|  |  | Photo taker | David | Alex S