## Sheet1
Name of event
Date, time
Location
Lead up to the event
Timestamp | Task | Time needed | Materials needed | Who's on point? | Notes
2 weeks before | Order DVD | 1 week to deliver | — | Teddy | Need to sign for delivery - account extra time in case logistics get complicated
2 days before | Print posters | 1 hour at Office Depot | Final PDF file, USB to transport | Teddy | Need this done before fellows can decorate them
During the event
Timestamp | Task | Time needed | Materials needed | Who's on point? | Notes
11:30 | Team arrives |  | — | All | Parade happening on 5th Ave. that day - leave extra time
11:35 | Move table from the closet | 5 min | Key to closet (Jerry has it) | Sue, Bill
11:45 | Coffee, snacks arrive |  | Alex's credit card | Kayla | Kayla should come to venue first to pick up Alex's credit card
12:30 | OFFICIAL START TIME
| Sign-in table | 20 min (12:30-12:50 | Three pens, three sign-in sheets, Action signs, flyers for next week's event | Kayla, Jerry
| Final sound, video check | 10 min (12:30-12:40) | A/V system | Teddy | Guests should not yet be in room - should be by snacks
12:40 | Usher guests into room | 5 min (12:40-45) | — | Sue | Make sure they take their seats and know program is about to begin
12:45 | Guest speaker | 15 min (12:45-12:50) | Microphone | Teddy (for A/V troubleshooting)
13:00 | Documentary begins | 90 min (1:00-2:30) | A/V system | Teddy (for A/V troubleshooting)
Post-event
Timestamp | Task | Time needed | Materials needed | Who's on point? | Notes
16:00 | Take trash out | 5 min | New trash bags | Jerry | New bags stored under kitchen sink
16:00 | Take extra signs, food to Alex's house | 30 min | Cab | Alex, Sue
16:15 | Final sweep | 5 min | — | Kayla | Return keys to office
This work is licensed under the Creative Commons Attribution-NonCommercial 4.0 International License. To view a copy of this license, visit http://creativecommons.org/licenses/by-nc/4.0/ or send a letter to Creative Commons, PO Box 1866, Mountain View, CA 94042, USA.